## GovCaptureAI_Roadmap
Phase | Sprint | Workstream | Deliverable | Status | Progress % | Priority | Demo Ready | Git/Artifact | Notes
Foundation | Sprint 1 | Project Setup | Create GovCaptureAI folder structure | Complete | 100 | High | Yes | Committed | Project folders created
Foundation | Sprint 1 | Git | Initialize repository and develop branch | Complete | 100 | High | Yes | Committed | Working tree clean
Documentation | Sprint 2 | Requirements | Product Requirements Specification | Complete | 100 | High | Yes | Docs created | Defines product vision
Documentation | Sprint 2 | Architecture | System Architecture document | Complete | 100 | High | Yes | Docs created | Defines FastAPI/PostgreSQL/Next.js architecture
Backend | Sprint 3 | FastAPI | Create backend app foundation | Complete | 100 | High | Yes | Committed | Swagger working
Backend | Sprint 3 | Swagger | Root endpoint and docs available | Complete | 100 | High | Yes | http://127.0.0.1:8000/docs | First live API demo
Database | Sprint 4A | PostgreSQL | Create database connection and health check | Complete | 100 | High | Yes | Committed | /health/database working
Database | Sprint 4B | Models | Create User Company Opportunity models | Complete | 100 | High | Yes | Committed | Initial domain models created
Database | Sprint 4B | Alembic | Create and apply initial migration | Complete | 100 | High | Yes | Committed | Tables verified in PostgreSQL
API | Sprint 4C | CRUD | Create Company API routes | Complete | 100 | High | Yes | Committed | GET and POST companies working
API | Sprint 4C | CRUD | Create Opportunity API routes | Complete | 100 | High | Yes | Committed | GET and POST opportunities working
SAM.gov | Sprint 5A | Mock Search | Create mock SAM.gov search endpoint | Complete | 100 | High | Yes | Committed | /api/v1/sam/search working
SAM.gov | Sprint 5B | Database Save | Save SAM search results to opportunities table | Complete | 100 | High | Yes | Committed | Mock search results saved
Capture Workflow | Sprint 5C | Opportunity Workflow | Add opportunity detail endpoint | Complete | 100 | High | Yes | Committed | GET opportunity by ID working
Capture Workflow | Sprint 5C | Status Workflow | Add opportunity status update endpoint | Complete | 100 | High | Yes | Committed | PATCH status working
Qualification | Sprint 5D | Scoring | Add manual opportunity score endpoint | Complete | 100 | High | Yes | Committed | Score and rationale saved
Dashboard | Sprint 5E | Summary | Add opportunity dashboard summary endpoint | Complete | 100 | High | Yes | Committed | Counts and average score working
SAM.gov Live | Sprint 6A | API Key | Add SAM.gov API configuration | Complete | 100 | High | Yes | Local .env | API key stored locally
SAM.gov Live | Sprint 6A | Live Test | Verify real SAM.gov API connection | Complete | 100 | High | Yes | Swagger live-test | status_code 200 confirmed
SAM.gov Live | Sprint 6B | Result Mapping | Map real SAM.gov results to internal format | Complete | 100 | High | Yes | Committed | Live SAM.gov result mapping hardened and tested
SAM.gov Live | Sprint 6C | Database Save | Save real SAM.gov opportunities to database | Complete | 100 | High | Yes | Committed | Live SAM.gov save flow working with duplicate prevention
Company Profile | Sprint 7A | Capabilities | Create company profile and capability fields | Complete | 100 | High | Yes | Committed | Company profile and capability fields added with profile update support
Knowledge Library | Sprint 7B | Documents | Upload capability and past performance documents | Complete | 100 | High | Yes | Committed | Knowledge library document endpoints added for qualification evidence
AI Qualification | Sprint 7C | Scoring Engine | Generate AI fit score 1-10 | Complete | 100 | High | Yes | Committed | Automatic qualification score endpoint added from company and opportunity fit
AI Qualification | Sprint 7D | Rationale | Generate AI score explanation | Complete | 100 | High | Yes | Committed | Recommendation and client-facing qualification rationale added for bid or no-bid review
Proposal | Sprint 8A | Draft Generator | Generate draft proposal response | Complete | 100 | High | Yes | Committed | Draft proposal response generator uses opportunity, company profile, qualification rationale, and document evidence
Proposal | Sprint 8B | Review Workflow | Track proposal review status | Complete | 100 | High | Yes | Committed | Proposal review workflow persists drafts, review status, readiness score, notes, and gaps
Frontend | Sprint 9A | Dashboard UI | Create web dashboard layout | Complete | 100 | High | Yes | Committed | Dashboard UI foundation exposes scores, recommendations, and rationale
Frontend | Sprint 9B | Opportunity UI | Display opportunity list and details | Complete | 100 | High | Yes | Committed | Opportunity review UI adds search, sorting, detail tabs, and qualification context
Frontend | Sprint 9C | Workflow UI | Update status and score from dashboard | Complete | 100 | High | Yes | Committed | Workflow UI adds status updates, auto-qualification actions, and notice-type filtering for RFI/RFQ/RFP/Sources Sought
Deployment | Sprint 10A | Raspberry Pi | Docker deployment preparation | Complete | 100 | Medium | Yes | Committed | Docker Compose demo stack added for PostgreSQL, FastAPI backend, and static dashboard frontend
Deployment | Sprint 10B | Demo Server | Run backend and database on demo server | Complete | 100 | Medium | Yes | Committed | Raspberry Pi demo server runbook and helper scripts added for sync, deploy, and health verification
Client Package | Sprint 11A | Sales Materials | Create product one-pager | Complete | 100 | High | Yes | docs/Sales | One-pager, demo script, and buyer FAQ created
Client Package | Sprint 11B | Proposal Export | Export proposal drafts to shareable document | Complete | 100 | High | Yes | API/UI export | Text export endpoint and dashboard download action added
Client Package | Sprint 11C | Demo Deck | Create sales presentation | Complete | 100 | High | Yes | docs/Sales/GovCaptureAI_Demo_Deck.pptx | Client-facing demo deck created for buyer meetings
Client Package | Sprint 11D | Pricing | Create consulting pricing model | Complete | 100 | Medium | Yes | docs/Sales/GovCaptureAI_Pricing_Model.xlsx | Pricing model and buyer-facing pricing brief created
Demo Polish | Sprint 12A | Live Demo | Polish demo environment and walkthrough | Complete | 100 | High | Yes | frontend/demo scripts/docs | Dashboard now identifies frontend source, API target, data mode, and build version; demo checker detects stale Pi frontend
Pilot Readiness | Sprint 12B | Buyer Walkthrough | Create a concise buyer walkthrough checklist and demo rehearsal flow | Planned | 0 | High | No | Planned | Revisit after marketing outreach identifies the first demo audience and objections
Go-To-Market | Sprint 12C | Marketing Pipeline | Create marketing plan, outreach copy, and demo prospect pipeline | Complete | 100 | High | Yes | docs/Sales | Marketing plan, outreach templates, and prospect pipeline workbook created to line up demos before Sprint 13A
Pilot Feedback | Sprint 13A | Buyer Feedback Loop | Analyze completed demos and convert buyer feedback into product priorities | Next | 0 | High | No | Planned | Start after 3 completed demos, 5 feedback items, and at least 1 serious pilot candidate or referral path
Pilot Feedback | Sprint 13B | Search-first Demo Hardening | Add SAM.gov result summaries and transparent fit score explanation | Planned | 0 | High | No | Planned | Buyer feedback: demo should start with actual SAM.gov search; results need short summaries; label scores as GovCaptureAI internal fit score, not government percentage.

## North_Star
GovCaptureAI North Star
Keep the roadmap tied to the real product objective: helping contractors discover, qualify, manage, and respond to federal opportunities with AI support.
Product Vision |  | North Star Checklist
1. Discover the right opportunities quickly |  | Does this sprint improve discovery, qualification, workflow, or proposal response?
2. Qualify whether the company should bid |  | Does it strengthen company-to-opportunity matching, not just data collection?
3. Manage the capture workflow with clarity |  | Does it move the product closer to a usable contractor dashboard or workflow?
4. Produce stronger proposal responses with AI assistance |  | Is this infrastructure serving capture management rather than becoming the goal?
Will the user be closer to a bid/no-bid or proposal outcome after this work?
Current Priority Path
Foundation complete | Live SAM.gov intake is now in place
Next product layer | Sprint 12C: Marketing and demo pipeline complete
Then | Work demo pipeline until Sprint 13A readiness gates are met
Then | Sprint 13A: Pilot feedback loop
Then | Authentication and team readiness
How to Read Progress
Complete | Directly usable in the contractor workflow or demo
Next | Highest-priority immediate product step
Planned | Important future step, but not the current bottleneck
High priority | Needed to unlock qualification, workflow, or proposal value
Demo Ready = Yes | Good enough to demonstrate as part of the product story
Decision Lens for Future Sprints
Good | This makes contractor decisions faster or better
Better | This improves AI-assisted qualification and rationale
Best | This clearly moves the product toward bid/no-bid and proposal outcomes
Avoid | Letting infrastructure milestones replace the product objective